## Release Data
| Release |  | R1 |  | R2 |  | R3 |  | R4 |  | R5 |  | R6
| Weeks | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  | 8
DEV
FNT
| MNT | [13 empty] | ...
| Team Size | 8 |  | 8 |  | 8 |  | 12 |  | 12 |  | 12 |  | 6
| Pair | 0 |  | 3 |  | 0 |  | 3 |  | 0 |  | 4 |  | 2
| Solo | 8 |  | 2 |  | 8 |  | 6 |  | 12 |  | 4 |  | 2
| Unit | 8 |  | 5 |  | 8 |  | 9 |  | 12 |  | 8 |  | 4
| %PP | 0% |  | 75% |  | 0% |  | 50% |  | 0% |  | 66.67% |  | 66.67%
| Release |  | R1 |  | R2 |  | R3 |  | R4 |  | R5 |  | R6
| Capacity | 3840 |  | 3840 |  | 3840 |  | 5760 |  | 5760 |  | 5760 |  | 1920 | p-hr
| DEV + FNT Effort | 2646 |  | 2906 |  | 2427 |  | 4536 |  | 4098 |  | 4612 |  | 0
| Minor MNT Effort | 384 |  | 480 |  | 426 |  | 523 |  | 640 |  | 523 |  | 384
[15 empty] | Done | Extra | Total
Major Bugs | R1 | 18 |  | 15 |  | 6 |  | 3 |  | 1 |  | 0 |  | 0 | 43 | 0 | 43
| R2 | - |  | 8 |  | 15 |  | 4 |  | 1 |  | 0 |  | 0 | 28 | 0 | 28
| R3 | - |  | - |  | 12 |  | 18 |  | 9 |  | 2 |  | 1 | 42 | 0 | 42
| R4 | - |  | - |  | - |  | 6 |  | 7 |  | 4 |  | 0 | 16 | 1 | 17
| R5 | - |  | - |  | - |  | - |  | 22 |  | 12 |  | 6 | 37 | 3 | 40
| R6 | - |  | - |  | - |  | - |  | - |  | 9 |  | 8 | 14 | 3 | 17
| Total | 18 |  | 23 |  | 33 |  | 31 |  | 40 |  | 27 |  | 15 | 180 | 7 | 187
Major MNT Effort | R1 | 810 |  | 630 |  | 234 |  | 114 |  | 42 |  | 0 |  | 0 | 1830 | 0 | 1830
| R2 | - |  | 304 |  | 675 |  | 156 |  | 39 |  | 0 |  | 0 | 1174 | 0 | 1174
| R3 | - |  | - |  | 504 |  | 684 |  | 342 |  | 78 |  | 39 | 1647 | 0 | 1647
| R4 | - |  | - |  | - |  | 270 |  | 315 |  | 152 |  | 0 | 737 | 46.0625 | 783.0625
| R5 | - |  | - |  | - |  | - |  | 924 |  | 540 |  | 252 | 1716 | 139.1351 | 1855.1351
| R6 | - |  | - |  | - |  | - |  | - |  | 378 |  | 312 | 690 | 147.8571 | 837.8571
| Total | 810 |  | 934 |  | 1413 |  | 1224 |  | 1662 |  | 1148 |  | 603 | 7794 | 333.0548 | 8127.0548
| Velocity (Pts) | 304 |  | 684 |  | 547 |  | 797 |  | 836 |  | 961 |  | 0 | 4129 | 0 | 4129
| Release |  | R1 |  | R2 |  | R3 |  | R4 |  | R5 |  | R6
| PP% | 0% |  | 75% |  | 0% |  | 50% |  | 0% |  | 66.67%
| Velocity (Pts) | 304 |  | 684 |  | 547 |  | 797 |  | 836 |  | 961
| Production Effort | 2646 |  | 2906 |  | 2427 |  | 4536 |  | 4098 |  | 4612 |  | (p-hr)
| Total Effort | 4476 |  | 4080 |  | 4074 |  | 5319.0625 |  | 5953.1351 |  | 5449.8571 |  | (p-hr)
| Efficiency | 59.12% |  | 71.23% |  | 59.57% |  | 85.28% |  | 68.84% |  | 84.63%
| Nom. Productivity | 4.5956 |  | 9.415 |  | 9.0152 |  | 7.0282 |  | 8.1601 |  | 8.3348 |  | (Pts/p-wk)
| Real Productivity | 2.7167 |  | 6.7059 |  | 5.3706 |  | 5.9935 |  | 5.6172 |  | 7.0534 |  | (Pts/p-wk)

## Benchmark Data
Data from | 12 | projects wity | 8 | releases each | = | 96 | releases
Teams of 6-12 people
R1 of each project excluded
Risk Category | Risk Cat. Id | Mean | StDev
External-Low | 1 | 7.9 | 0.6
External-Medium | 2 | 5.6 | 0.9
External-High | 3 | 3.8 | 2.1
| Release Id | Velocity | Risk Category | Low Risk | Med Risk | High Risk
| (Start Date Seq#) | (Pts/p-week)
| 1 | 6.0944 | 3 |  |  | 6.0944
| 2 | 5.092 | 2 |  | 5.092
| 3 | 7.9473 | 1 | 7.9473
| 4 | 5.4332 | 2 |  | 5.4332
| 5 | 6.6988 | 1 | 6.6988
| 6 | 7.7797 | 1 | 7.7797
| 7 | 3.9503 | 3 |  |  | 3.9503
| 8 | 3.8255 | 3 |  |  | 3.8255
| 9 | 4.5581 | 2 |  | 4.5581
| 10 | 1.6431 | 3 |  |  | 1.6431
| 11 | 7.7058 | 1 | 7.7058
| 12 | 3.0407 | 3 |  |  | 3.0407
| 13 | 6.2712 | 2 |  | 6.2712
| 14 | 4.1268 | 2 |  | 4.1268
| 15 | 6.2873 | 2 |  | 6.2873
| 16 | 5.6002 | 2 |  | 5.6002
| 17 | 7.0405 | 1 | 7.0405
| 18 | 7.193 | 1 | 7.193
| 19 | 8.9313 | 1 | 8.9313
| 20 | 8.0137 | 1 | 8.0137
| 21 | 7.8164 | 1 | 7.8164
| 22 | 7.0205 | 2 |  | 7.0205
| 23 | 5.3476 | 2 |  | 5.3476
| 24 | 5.0922 | 2 |  | 5.0922
| 25 | 5.3242 | 2 |  | 5.3242
| 26 | 6.5503 | 2 |  | 6.5503
| 27 | 5.7301 | 2 |  | 5.7301
| 28 | 6.5084 | 2 |  | 6.5084
| 29 | 4.7143 | 2 |  | 4.7143
| 30 | 2.975 | 3 |  |  | 2.975
| 31 | 7.9339 | 1 | 7.9339
| 32 | 5.4213 | 2 |  | 5.4213
| 33 | 6.5909 | 2 |  | 6.5909
| 34 | 5.6011 | 2 |  | 5.6011
| 35 | 2.5159 | 3 |  |  | 2.5159
| 36 | 6.5337 | 2 |  | 6.5337
| 37 | 5.3856 | 3 |  |  | 5.3856
| 38 | 4.4255 | 2 |  | 4.4255
| 39 | 5.8578 | 2 |  | 5.8578
| 40 | 1.6378 | 3 |  |  | 1.6378
| 41 | 6.6726 | 2 |  | 6.6726
| 42 | 8.5263 | 1 | 8.5263
| 43 | 7.8607 | 1 | 7.8607
| 44 | 6.997 | 1 | 6.997
| 45 | 5.2034 | 2 |  | 5.2034
| 46 | 6.1288 | 2 |  | 6.1288
| 47 | 5.8779 | 2 |  | 5.8779
| 48 | 4.921 | 2 |  | 4.921
| 49 | 8.2612 | 1 | 8.2612
| 50 | 5.8116 | 2 |  | 5.8116
| 51 | 8.4647 | 2 |  | 8.4647
| 52 | 7.3557 | 2 |  | 7.3557
| 53 | 6.9992 | 2 |  | 6.9992
| 54 | 4.4218 | 2 |  | 4.4218
| 55 | 6.7298 | 2 |  | 6.7298
| 56 | 4.2697 | 3 |  |  | 4.2697
| 57 | 2.7263 | 3 |  |  | 2.7263
| 58 | 5.7588 | 2 |  | 5.7588
| 59 | 3.9592 | 2 |  | 3.9592
| 60 | 5.3719 | 2 |  | 5.3719
| 61 | 8.3755 | 1 | 8.3755
| 62 | 6.0295 | 3 |  |  | 6.0295
| 63 | 7.793 | 1 | 7.793
| 64 | 7.9474 | 1 | 7.9474
| 65 | 5.6839 | 2 |  | 5.6839
| 66 | 7.095 | 2 |  | 7.095
| 67 | 6.5128 | 2 |  | 6.5128
| 68 | 4.9357 | 2 |  | 4.9357
| 69 | 6.0045 | 2 |  | 6.0045
| 70 | 5.3019 | 2 |  | 5.3019
| 71 | 2.5553 | 3 |  |  | 2.5553
| 72 | 5.0193 | 2 |  | 5.0193
| 73 | 4.2259 | 2 |  | 4.2259
| 74 | 4.9251 | 2 |  | 4.9251
| 75 | 7.6825 | 1 | 7.6825
| 76 | 5.2296 | 2 |  | 5.2296
| 77 | 8.4231 | 1 | 8.4231
| 78 | 5.09 | 2 |  | 5.09
| 79 | 8.302 | 1 | 8.302
| 80 | 4.9951 | 2 |  | 4.9951
| 81 | 6.549 | 2 |  | 6.549
| 82 | 1 | 3 |  |  | 1
| 83 | 5.7974 | 2 |  | 5.7974
| 84 | 6.9932 | 2 |  | 6.9932
| 85 | 7.4695 | 1 | 7.4695
| 86 | 2.6872 | 3 |  |  | 2.6872
| 87 | 8.0112 | 1 | 8.0112
| 88 | 7.4831 | 1 | 7.4831
| 89 | 4.8166 | 3 |  |  | 4.8166
| 90 | 5.6304 | 2 |  | 5.6304
| 91 | 7.3157 | 2 |  | 7.3157
| 92 | 7.6355 | 2 |  | 7.6355
| 93 | 8.0696 | 1 | 8.0696
| 94 | 5.3187 | 2 |  | 5.3187
| 95 | 4.5023 | 2 |  | 4.5023
| 96 | 1.1981 | 3 |  |  | 1.1981
|  |  | Mean | 7.8443 | 5.755 | 3.3148
|  |  | StDev | 0.51954 | 0.96931 | 1.597

## Analysis
Benchmark real productivity for project teams of 6-12 in same risk category
0% | PP usage
5.6 | Story Pts/p-wk
Relative to Benchmark
|  | Min Improvement | 7.027%
|  | Max Improvement | 25.95%
Total number of developers in MedSoft |  |  |  | 300
Average salary of MedSoft developer |  |  |  | 125 | K/year
PP Training Cost for TrialWeb Team |  |  |  | 30 | K |  | NPV in PI risk category at |  | ROI in PV Terms
Total PP Training Cost |  |  |  | 750 | K |  | 20% | discount rate
Savings @ Min Improvement |  |  |  | 2635.2951 | K/year | Þ | 15061.7703 | K | 20.0824
Savings @ Max Improvement |  |  |  | 9732.5618 | K/year | Þ | 57645.3708 | K | 76.8605

## Magic Numbers
p | 45
q | 42
t | 38
s | 39
a | 19
w | 40